## General
ZELDA: HYRULE CONQUEST
Summit Games
Project Lead: |  | Nicolas Babot
Project Start Date: |  | 2017-02-13 | time axis 2017-02-13 to 2017-06-03
Display Week: |  | 1 |  |  |  |  | 2017-02-20: Week 2; 2017-02-27: Week 3; 2017-03-06: Week 4; 2017-03-13: Week 5; 2017-03-20: Week 6; 2017-03-27: Week 7; 2017-04-03: Week 8; 2017-04-10: Week 9; 2017-04-17: Week 10; 2017-04-24: Week 11; 2017-05-01: Week 12; 2017-05-08: Week 13; 2017-05-15: Week 14; 2017-05-22: Week 15; 2017-05-29: Week 16
[7 empty] | 2017-02-13 | [6 empty] | 2017-02-20 | [6 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27 | [6 empty] | 2017-04-03 | [6 empty] | 2017-04-10 | [6 empty] | 2017-04-17 | [6 empty] | 2017-04-24 | [6 empty] | 2017-05-01 | [6 empty] | 2017-05-08 | [6 empty] | 2017-05-15 | [6 empty] | 2017-05-22 | [6 empty] | 2017-05-29
Task | Lead | Start | End | hours estimated | % deviation | Hours | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Core engine | Miquel Izquierdo
Windows Resized |  | 2017-02-13 | 2017-02-15 | 1 | 100% | 1 | bar: 2017-02-13 T to 2017-02-13 W
Module Scene |  | 2017-02-14 | 2017-02-16 | 1 | 100% | 1 | bar: 2017-02-13 T to 2017-02-13 W
Console Code | Xavier Olivenza
Creating the Module console |  | 2017-02-13 | 2017-02-23 | 25 | 80% | 20
Adding to Project master |  | 2017-02-24 | 2017-02-24 | 4 | 75% | 3
Extracting Sprites | Daniel Olondriz
Overworld Spriites |  | 2017-02-14 | 2017-02-14 | 10 | 70% | 7
Overworld Spriites |  | 2017-02-14 | 2017-02-15 | 6 | 83.33% | 5
Link sprites extract | Guillermo Pinto
Link sprites |  | 2017-02-14 | 2017-02-15 | 8 | 62.5% | 5
Players | Miquel Izquierdo
Player |  | 2017-02-15 | 2017-02-15 | 1 | 100% | 1
2nd player |  | 2017-02-15 | 2017-02-16 | 2 | 100% | 2
Code to STD | Nicolas babot
Coding STD |  | 2017-02-16 | 2017-02-17 | 4 | 112.5% | 4.5
Trello, github and management | Guillermo Pinto
Trello,github and management tools |  | 2017-02-18 | 2017-02-18 | 5 | 120% | 6
Overworld tileset | Daniel Olondriz
change tileset |  | 2017-02-18 | 2017-02-18 | 1 | 200% | 2
dungeon tileset |  | 2017-02-18 | 2017-02-19 | 2 | 100% | 2
Boss design |  | 2017-02-18 | 2017-02-26 | 20 | 100% | 20
Players | Miquel Izquierdo
Player |  | 2017-02-19 | 2017-02-20 | 2 | 100% | 2
Move Player |  | 2017-02-19 | 2017-02-22 | 1 | 300% | 3
Players | Miquel Izquierdo
Pathfinding |  | 2017-02-21 | 2017-02-24 | 4 | 75% | 3
Pathfinding | Nicolas babot | 2017-02-22 | 2017-02-23 | 2 | 100% | 2
Window | Nicolas babot
Animation, fade to black |  | 2017-02-24 | 2017-02-24 | 2 | 100% | 2
Camera limits |  | 2017-02-24 | 2017-02-25 | 4 | 100% | 4
Players | Miquel Izquierdo
2 player mode |  | 2017-02-28 | 2017-02-28 | 3 | 100% | 3
Link sprites extract | Guillermo Pinto
Link sprites extract |  | 2017-02-28 | 2017-02-28 | 5 | 120% | 6
Window | Xavier Olivenza
Window resize |  | 2017-02-28 | 2017-02-28 | 3 | 66.67% | 2
Animation, fade to black | Miquel Izquierdo
Link animation add |  | 2017-03-01 | 2017-03-02 | 3 | 100% | 3
Production Plan | Team
Production Plan |  | 2017-03-02 | 2017-03-06 | 20 | 125% | 25
Movement | Miquel Izquierdo
Animations for 2 players |  | 2017-03-07 | 2017-03-07 | 3 | 166.7% | 5
Movement |  | 2017-03-07 | 2017-03-13 | 6 | 83.33% | 5
Window | Xavier Olivenza
diagrams |  | 2017-03-07 | 2017-03-07 | 3 | 66.67% | 2
Player | Miquel Izquierdo
character and player reestructured |  | 2017-03-08 | 2017-03-08 | 4 | 75% | 3
Menu | Nicolas babot
Enable disable menu |  | 2017-03-13 | 2017-03-13 | 1 | 200% | 2
Production!
Link sprites | Guillermo Pinto
Link sprites, bigger |  | 2017-03-13 | 2017-03-13 | 6 | 100% | 6
bug hunting | Adrian Higuero
bug hunting |  | 2017-03-13 | 2017-03-19 | 3 | 100% | 3
Camara | Xavier Olivenza
Elipses and centring |  | 2017-03-13 | 2017-03-19 | 15 | 113.3% | 17
Height and jump | Miquel Izquierdo
player stats |  | 2017-03-14 | 2017-03-14 | 2 | 50% | 1
Levels of height |  | 2017-03-14 | 2017-03-15 | 3 | 100% | 3
Jump |  | 2017-03-14 | 2017-03-15 | 2 | 100% | 2
Collider | Nicolas babot
Logic |  | 2017-03-14 | 2017-03-16 | 2 | 100% | 2
M.Collision |  | 2017-03-14 | 2017-03-16 | 3 | 100% | 3
Link Collider |  | 2017-03-14 | 2017-03-16 | 3 | 66.67% | 2
Height Collider |  | 2017-03-14 | 2017-03-16 | 1 | 200% | 2
Gamepad | Javier ortiz
Gamepad |  | 2017-03-15 | 2017-03-16 | 3 | 133.3% | 4
bug hunting | Adrian Higuero
bug hunting |  | 2017-03-16 | 2017-03-16 | 3 | 100% | 3
Link sprites | Guillermo Pinto
Link sprites, bigger |  | 2017-03-16 | 2017-03-16 | 6 | 100% | 6
zoom | Miquel Izquierdo
zoom |  | 2017-03-16 | 2017-03-16 | 3 | 66.67% | 2
bugs |  | 2017-03-16 | 2017-03-16 | 5 | 20% | 1
Roll and entities | Miquel Izquierdo
Roll implemented |  | 2017-03-17 | 2017-03-17 | 3 | 66.67% | 2
Collision and entities |  | 2017-03-17 | 2017-03-17 | 3 | 100% | 3
player heigth |  | 2017-03-18 | 2017-03-18 | 1 | 200% | 2
re sized map |  | 2017-03-18 | 2017-03-19 | 4 | 75% | 3
Buttons | Nicolas babot
Buttons implemented |  | 2017-03-18 | 2017-03-18 | 3 | 66.67% | 2
zelda | Daniel Olondriz
Zelda sprites |  | 2017-03-19 | 2017-03-19 | 3 | 133.3% | 4
zelda add | Miquel Izquierdo
Zelda sprites added |  | 2017-03-19 | 2017-03-19 | 2 | 50% | 1
zelda jump and roll |  | 2017-03-19 | 2017-03-19 | 2 | 100% | 2
collision tiles and print |  | 2017-03-19 | 2017-03-19 | 2 | 50% | 1
item tileset | Guillermo Pinto
item tileset |  | 2017-03-19 | 2017-03-19 | 6 | 83.33% | 5
Game puzzles | Javier ortiz
Game puzzles |  | 2017-03-15 | 2017-03-16 | 6 | 66.67% | 4
coperative & culling | Nicolas babot
cooperartive game |  | 2017-03-19 | 2017-03-19 | 2 | 150% | 3
Camera culling |  | 2017-03-19 | 2017-03-21 | 5 | 80% | 4
Camara | Xavier Olivenza
zoom camera |  | 2017-03-19 | 2017-03-19 | 3 | 100% | 3
Gui variablles |  | 2017-03-19 | 2017-03-20 | 3 | 33.33% | 1
debug mode |  | 2017-03-19 | 2017-03-21 | 3 | 100% | 3
bug hunting | Adrian Higuero
bug hunting |  | 2017-03-23 | 2017-03-23 | 3 | 100% | 3
Picking zelda | Miquel Izquierdo
Picking zelda |  | 2017-03-23 | 2017-03-23 | 2 | 150% | 3
Link sprites | Guillermo Pinto
Link sprites, bigger |  | 2017-03-16 | 2017-03-16 | 5 | 60% | 3
throwing zelda |  | 2017-03-23 | 2017-03-27 | 2 | 150% | 3
Enemies | Nicolas babot
Enemies, enemies by tiles |  | 2017-03-23 | 2017-03-28 | 12 | 125% | 15
Menu | Xavier Olivenza
Main menu,options |  | 2017-03-23 | 2017-03-24 | 4 | 125% | 5
Gamepad | Javier ortiz
second gamepad |  | 2017-03-24 | 2017-03-24 | 4 | 75% | 3
HUD | Xavier Olivenza
Hud module |  | 2017-03-27 | 2017-03-27 | 2 | 100% | 2
Life add |  | 2017-03-28 | 2017-03-28 | 2 | 50% | 1
bug hunting | Adrian Higuero
bug hunting |  | 2017-03-28 | 2017-03-28 | 3 | 100% | 3
Arrows | Miquel Izquierdo
Arrows |  | 2017-03-28 | 2017-03-29 | 5 | 140% | 7
Puzzles | Javier ortiz
1rst puzzle |  | 2017-03-28 | 2017-03-30 | 1 | 200% | 2
2nd puzzle |  | 2017-03-28 | 2017-03-30 | 2 | 100% | 2
3rd puzzle |  | 2017-03-28 | 2017-03-30 | 1 | 300% | 3
Graphic Menu | Daniel Olondriz
Graphic menu |  | 2017-03-28 | 2017-03-28 | 3 | 100% | 3
Enemies | Nicolas babot
Sword collision |  | 2017-03-29 | 2017-03-29 | 8 | 75% | 6
Intro, mmain menu parralax | Xavier Olivenza
background intro, parrallax |  | 2017-03-29 | 2017-03-29 | 6 | 133.3% | 8
item tileset | Guillermo Pinto
item tileset |  | 2017-03-29 | 2017-03-29 | 5 | 80% | 4
dungeon tileset | Daniel Olondriz
dungeon tileset |  | 2017-03-29 | 2017-03-29 | 5 | 80% | 4
bug hunting | Adrian Higuero
bug hunting |  | 2017-03-30 | 2017-03-30 | 3 | 100% | 3
menu atlas | Xavier Olivenza
menu atlas |  | 2017-03-30 | 2017-03-30 | 2 | 50% | 1
social buttons added |  | 2017-03-30 | 2017-03-30 | 2 | 50% | 1
Picking zelda | Miquel Izquierdo
Animations pivot, maps |  | 2017-03-30 | 2017-03-30 | 3 | 133.3% | 4
dungeon tileset | Daniel Olondriz
Dunngeon tileset |  | 2017-03-30 | 2017-03-30 | 3 | 100% | 3
collision tileset |  | 2017-03-30 | 2017-03-31 | 4 | 125% | 5
Enemies | Nicolas babot
Sword-enemies collision |  | 2017-03-30 | 2017-03-30 | 2 | 100% | 2
Sharing art | Adrian Higuero
twitter and github button |  | 2017-03-30 | 2017-03-30 | 3 | 66.67% | 2
link spritesheet | Guillermo Pinto
link spritesheet |  | 2017-03-30 | 2017-03-31 | 5 | 120% | 6
Gamepad | Javier ortiz
gamepad |  | 2017-03-30 | 2017-03-31 | 4 | 75% | 3
tiled | Xavier Olivenza
tiled |  | 2017-03-31 | 2017-03-31 | 1 | 100% | 1
Enemies | Nicolas babot
Enemies |  | 2017-03-31 | 2017-03-31 | 3 | 66.67% | 2
In game | Miquel Izquierdo
map update, change scene |  | 2017-03-31 | 2017-04-01 | 2 | 100% | 2
objects with texture |  | 2017-03-31 | 2017-03-31 | 2 | 50% | 1
more arrows |  | 2017-03-31 | 2017-04-01 | 1 | 100% | 1
door |  | 2017-03-31 | 2017-04-01 | 4 | 75% | 3
pathfinding | Nicolas babot
pathfinding |  | 2017-04-01 | 2017-04-01 | 3 | 166.7% | 5
in game menu | Xavier Olivenza
in game menu |  | 2017-04-01 | 2017-04-02 | 6 | 116.7% | 7
spritesheet link | Daniel Olondriz
spritesheet link |  | 2017-04-01 | 2017-04-01 | 1 | 200% | 2
audio and enemy | Nicolas babot
Audio |  | 2017-04-01 | 2017-04-01 | 1 | 200% | 2
enemy path |  | 2017-04-01 | 2017-04-02 | 3 | 100% | 3
link, zelda, attack | Miquel Izquierdo
Link update |  | 2017-04-01 | 2017-04-01 | 1 | 100% | 1
Zelda Attack |  | 2017-04-01 | 2017-04-01 | 1 | 100% | 1
Attack timing |  | 2017-04-01 | 2017-04-01 | 2 | 50% | 1
audio and enemy | Nicolas babot
Controls |  | 2017-04-02 | 2017-04-02 | 1 | 200% | 2
Tileset puzzles | Javier ortiz
tileset puzzle 1 |  | 2017-04-02 | 2017-04-02 | 2 | 150% | 3
tileset puzzle 2 |  | 2017-04-02 | 2017-04-02 | 2 | 200% | 4
sprites | Daniel Olondriz
Zelda (blue link) |  | 2017-04-02 | 2017-04-02 | 2 | 50% | 1
Dianas |  | 2017-04-02 | 2017-04-02 | 1 | 100% | 1
Bow |  | 2017-04-02 | 2017-04-02 | 1 | 200% | 2
controls menu |  | 2017-04-02 | 2017-04-02 | 1 | 100% | 1
spritesheet | Guillermo Pinto
enemies spritesheets |  | 2017-04-02 | 2017-04-02 | 5 | 120% | 6
Appveyor | Adrian Higuero
Appveyor implementation |  | 2017-04-02 | 2017-04-02 | 1 | 200% | 2
init variables to zero | Guillermo Pinto
initing variables |  | 2017-04-02 | 2017-04-02 | 2 | 150% | 3
code to STD |  | 2017-04-02 | 2017-04-02 | 4 | 75% | 3
bug hunting, player collider | Nicolas babot
bug fixing |  | 2017-04-03 | 2017-04-03 | 2 | 150% | 3
player collider |  | 2017-04-03 | 2017-04-03 | 3 | 100% | 3
Game loop art, scenes | Daniel Olondriz
Game loop art |  | 2017-04-03 | 2017-04-03 | 4 | 75% | 3
Scenes |  | 2017-04-03 | 2017-04-03 | 2 | 150% | 3
Bug hunting, pause, draw | Miquel Izquierdo
fixing bugs |  | 2017-04-03 | 2017-04-03 | 2 | 50% | 1
pause |  | 2017-04-03 | 2017-04-03 | 2 | 100% | 2
Draw function |  | 2017-04-03 | 2017-04-03 | 3 | 66.67% | 2
Gamepad | Javier ortiz
gamepad |  | 2017-04-03 | 2017-04-03 | 5 | 80% | 4
Bug hunting | Adrian Higuero
Bug hunting |  | 2017-04-03 | 2017-04-03 | 3 | 166.7% | 5
in game menu | Xavier Olivenza
in game menu |  | 2017-04-03 | 2017-04-03 | 1 | 100% | 1
xml |  | 2017-04-03 | 2017-04-03 | 1 | 100% | 1
Load code |  | 2017-04-03 | 2017-04-03 | 3 | 66.67% | 2
Scenes |  | 2017-04-03 | 2017-04-03 | 1 | 100% | 1
Menu label |  | 2017-04-04 | 2017-04-04 | 4 | 50% | 2
Backgound |  | 2017-04-04 | 2017-04-04 | 1 | 200% | 2
HUD |  | 2017-04-04 | 2017-04-04 | 3 | 66.67% | 2
bug hunting | Adrian Higuero
bug hunting |  | 2017-04-04 | 2017-04-04 | 3 | 133.3% | 4
Loop, life, sound effect | Nicolas babot
Loop |  | 2017-04-04 | 2017-04-04 | 2 | 100% | 2
Life add |  | 2017-04-04 | 2017-04-04 | 1 | 200% | 2
Sound Efect |  | 2017-04-04 | 2017-04-04 | 2 | 100% | 2
door sprites, title and controls | Daniel Olondriz
Door sprites |  | 2017-04-04 | 2017-04-04 | 1 | 100% | 1
Title sprites |  | 2017-04-04 | 2017-04-04 | 2 | 100% | 2
Controls |  | 2017-04-04 | 2017-04-04 | 1 | 100% | 1
Gamepad | Javier ortiz
gamepad |  | 2017-04-04 | 2017-04-04 | 3 | 100% | 3
Bug hunting, pause, draw | Miquel Izquierdo
Arrows |  | 2017-04-04 | 2017-04-04 | 1 | 200% | 2
Hits effects |  | 2017-04-04 | 2017-04-04 | 2 | 100% | 2
Maps |  | 2017-04-04 | 2017-04-04 | 1 | 200% | 2
Link sprites, bigger | Guillermo Pinto
Link spritesheets |  | 2017-04-04 | 2017-04-05 | 12 | 83.33% | 10
Menu and music sync | Xavier Olivenza
Menu and music sync |  | 2017-04-05 | 2017-04-05 | 4 | 100% | 4
Button sprites, audio | Daniel Olondriz
Button sprites, audio |  | 2017-04-05 | 2017-04-05 | 5 | 80% | 4
bugs, collider | Nicolas babot
Collider |  | 2017-04-05 | 2017-04-05 | 3 | 133.3% | 4
Bug hunting, pause, draw | Miquel Izquierdo
attack bugs |  | 2017-04-05 | 2017-04-05 | 5 | 80% | 4
bug hunting | Adrian Higuero
bug hunting |  | 2017-04-06 | 2017-04-06 | 3 | 133.3% | 4
Coming soon sign | Xavier Olivenza
Coming soon sign |  | 2017-04-06 | 2017-04-06 | 3 | 66.67% | 2
Dialogue manager |  | 2017-04-06 | 2017-04-07 | 3 | 133.3% | 4
Module action | Miquel Izquierdo
Module action |  | 2017-04-06 | 2017-04-06 | 2 | 100% | 2
tileset village | Javier ortiz
tileset village |  | 2017-04-06 | 2017-04-10 | 5 | 240% | 12
Tilesets created | Guillermo Pinto
Tileset created |  | 2017-04-14 | 2017-04-14 | 7 | 85.71% | 6
Items and overworld tileset | Daniel Olondriz
items and overworld tileset |  | 2017-04-14 | 2017-04-14 | 4 | 75% | 3
Green Enemy | Nicolas babot
Green Enemy |  | 2017-04-16 | 2017-04-16 | 3 | 100% | 3
Collision tileset | Daniel Olondriz
Collision tileset |  | 2017-04-17 | 2017-04-17 | 6 | 66.67% | 4
design dungeon | Javier ortiz
design dungeon |  | 2017-04-17 | 2017-04-19 | 3 | 100% | 3
Green Enemy | Nicolas babot
Green Enemy |  | 2017-04-17 | 2017-04-19 | 5 | 80% | 4
Fran research | Xavier Olivenza
Fran research |  | 2017-04-18 | 2017-04-18 | 4 | 75% | 3
Module action | Miquel Izquierdo
arrow directions |  | 2017-04-18 | 2017-04-18 | 3 | 66.67% | 2
Coming soon sign | Xavier Olivenza
Dialogue manager |  | 2017-04-21 | 2017-04-21 | 6 | 100% | 6
Green Enemy | Nicolas babot
enemies, shield bomb |  | 2017-04-21 | 2017-04-21 | 5 | 120% | 6
bomb enemy |  | 2017-04-22 | 2017-04-22 | 4 | 75% | 3
tileset woods | Javier ortiz
tileset woods |  | 2017-04-22 | 2017-04-22 | 4 | 150% | 6
dialogues xml | Xavier Olivenza
Dialogues XML |  | 2017-04-22 | 2017-04-22 | 2 | 100% | 2
items read, npc |  | 2017-04-22 | 2017-04-23 | 2 | 200% | 4
Boss | Miquel Izquierdo
Test room and boos |  | 2017-04-22 | 2017-04-22 | 3 | 133.3% | 4
boss foots |  | 2017-04-23 | 2017-04-23 | 3 | 100% | 3
Green Enemy | Nicolas babot
Enemies Collision |  | 2017-04-23 | 2017-04-23 | 4 | 75% | 3
Dialogues | Adrian Higuero
Dialogues |  | 2017-04-23 | 2017-04-25 | 10 | 100% | 10
Quadtree | Xavier Olivenza
Quadtree |  | 2017-04-24 | 2017-04-24 | 2 | 100% | 2
Adapting blit |  | 2017-04-24 | 2017-04-25 | 1 | 100% | 1
Puzzle | Miquel Izquierdo
color puzzle |  | 2017-04-24 | 2017-04-24 | 2 | 150% | 3
Puzzle color | Javier ortiz
Puzzle color |  | 2017-04-24 | 2017-04-24 | 2 | 100% | 2
Dungeon, int and ex castle | Guillermo Pinto
Tilesets created |  | 2017-04-24 | 2017-04-24 | 6 | 100% | 6
Cave tileset |  | 2017-04-24 | 2017-04-25 | 2 | 150% | 3
Dialogues illustration | Daniel Olondriz
Dialogue illustration |  | 2017-04-24 | 2017-04-26 | 6 | 83.33% | 5
Dialogues | Adrian Higuero
Dialogues |  | 2017-04-25 | 2017-04-29 | 8 | 125% | 10
Enemies spritesheet hit | Guillermo Pinto
Enemies spritesheet hit |  | 2017-04-26 | 2017-04-26 | 2 | 150% | 3
save/load code | Xavier Olivenza
save / load |  | 2017-04-27 | 2017-04-27 | 4 | 100% | 4
Enemies | Nicolas babot
On collisionn |  | 2017-04-27 | 2017-04-27 | 2 | 100% | 2
Arnus enemy |  | 2017-04-27 | 2017-04-27 | 3 | 100% | 3
Dialogues illustration | Daniel Olondriz
Dialogue illustration |  | 2017-04-27 | 2017-04-27 | 3 | 200% | 6
fixing collision module | Miquel Izquierdo
fixing collison module |  | 2017-04-28 | 2017-04-28 | 1 | 100% | 1
Boss |  | 2017-04-28 | 2017-05-01 | 7 | 128.6% | 9
testing scenes and sprites | Nicolas babot
testing scenes and adding spirtes |  | 2017-04-28 | 2017-04-28 | 2 | 100% | 2
Scenes |  | 2017-04-29 | 2017-04-29 | 3 | 200% | 6
zelda sprites | Daniel Olondriz
zelda spites |  | 2017-04-29 | 2017-04-29 | 3 | 200% | 6
maps | Miquel Izquierdo
maps |  | 2017-04-30 | 2017-04-30 | 2 | 100% | 2
arnus snake | Nicolas babot
arnus snake |  | 2017-04-30 | 2017-05-01 | 2 | 150% | 3
Dialogues | Adrian Higuero
Dialogues |  | 2017-05-01 | 2017-05-01 | 4 | 100% | 4
quadtree and particles | Xavier Olivenza
quadtree and particles |  | 2017-05-03 | 2017-05-04 | 15 | 80% | 12
Dialogues illustration | Daniel Olondriz
Dialogue illustration |  | 2017-05-06 | 2017-05-06 | 4 | 100% | 4
camera, atlas, dialogues… | Xavier Olivenza
camera fix |  | 2017-05-06 | 2017-05-06 | 2 | 50% | 1
atlas |  | 2017-05-06 | 2017-05-06 | 2 | 50% | 1
module dialogue |  | 2017-05-06 | 2017-05-06 | 2 | 100% | 2
add function |  | 2017-05-06 | 2017-05-06 | 2 | 100% | 2
menus |  | 2017-05-06 | 2017-05-06 | 1 | 100% | 1
memory leaks |  | 2017-05-06 | 2017-05-06 | 1 | 100% | 1
Enemies spritesheet hit | Guillermo Pinto
secret exit map |  | 2017-05-06 | 2017-05-06 | 4 | 150% | 6
cutscenes, enemy | Nicolas babot
cutscenes, enemy |  | 2017-05-06 | 2017-05-08 | 4 | 400% | 16
Boss, bug hunting | Miquel Izquierdo
boss |  | 2017-05-06 | 2017-05-06 | 4 | 100% | 4
bug hunting |  | 2017-05-06 | 2017-05-07 | 4 | 100% | 4
Zelda XML | Guillermo Pinto
Zelda xml pivot |  | 2017-05-07 | 2017-05-07 | 2 | 100% | 2
Dialogues illustration | Daniel Olondriz
Dialogue illustration |  | 2017-05-07 | 2017-05-07 | 4 | 175% | 7
Dialogues | Adrian Higuero
Dialogues |  | 2017-05-08 | 2017-05-09 | 6 | 150% | 9
Boss, bug hunting | Miquel Izquierdo
boss |  | 2017-05-08 | 2017-05-08 | 6 | 133.3% | 8
Inside house | Guillermo Pinto
insidue house |  | 2017-05-08 | 2017-05-08 | 8 | 100% | 8
enemy | Nicolas babot
enemy path |  | 2017-05-09 | 2017-05-09 | 5 | 100% | 5
before dungeon and puzzle | Guillermo Pinto
before dungeon and puzzle |  | 2017-05-09 | 2017-05-09 | 6 | 66.67% | 4
Dialogues illustration | Daniel Olondriz
Dialogue illustration |  | 2017-05-09 | 2017-05-09 | 8 | 75% | 6
Boss | Miquel Izquierdo
Boss |  | 2017-05-09 | 2017-05-10 | 8 | 100% | 8
Second control setting | Javier ortiz
Second control setting |  | 2017-05-09 | 2017-05-09 | 2 | 100% | 2
bug hunting |  | 2017-05-10 | 2017-05-10 | 2 | 150% | 3
XML dialogues | Xavier Olivenza
XML dialogues, NPC, camera |  | 2017-05-10 | 2017-05-10 | 5 | 120% | 6
alternative controller |  | 2017-05-10 | 2017-05-10 | 3 | 66.67% | 2
maps, tiles and fixing, cutscenes | Nicolas babot
tile, cameras, maps |  | 2017-05-10 | 2017-05-10 | 5 | 120% | 6
cutscenes |  | 2017-05-10 | 2017-05-10 | 3 | 66.67% | 2
before dungeon and puzzle | Guillermo Pinto
navy sprites and lake |  | 2017-05-10 | 2017-05-10 | 4 | 100% | 4
throne room added |  | 2017-05-10 | 2017-05-10 | 3 | 133.3% | 4
Dialogues illustration | Daniel Olondriz
Dialogue illustration |  | 2017-05-10 | 2017-05-10 | 4 | 75% | 3
Intro and sounds |  | 2017-05-10 | 2017-05-10 | 3 | 166.7% | 5
bug hunting | Adrian Higuero
bug hunting |  | 2017-05-11 | 2017-05-11 | 3 | 133.3% | 4
NPC and cutscenes | Nicolas babot
NPC, helping and cutscenes |  | 2017-05-11 | 2017-05-11 | 8 | 100% | 8
cutscenes, | Guillermo Pinto
cutscenes xml |  | 2017-05-11 | 2017-05-12 | 16 | 100% | 16
cinematics | Daniel Olondriz
cinematics |  | 2017-05-11 | 2017-05-11 | 6 | 66.67% | 4
music to OGG |  | 2017-05-11 | 2017-05-11 | 6 | 83.33% | 5
Boss | Miquel Izquierdo
Boss |  | 2017-05-11 | 2017-05-11 | 6 | 116.7% | 7
Top of the mountain, path to boss |  | 2017-05-11 | 2017-05-11 | 2 | 50% | 1
XML dialogues | Xavier Olivenza
dialogues, save |  | 2017-05-11 | 2017-05-12 | 7 | 142.9% | 10
bug fixing |  | 2017-05-11 | 2017-05-11 | 1 | 100% | 1
bug fixing | Miquel Izquierdo
bug fixing |  | 2017-05-12 | 2017-05-12 | 2 | 50% | 1
Boss, maps |  | 2017-05-12 | 2017-05-12 | 5 | 140% | 7
NPC | Nicolas babot
NPC |  | 2017-05-12 | 2017-05-12 | 3 | 133.3% | 4
save / load |  | 2017-05-12 | 2017-05-12 | 5 | 80% | 4
cutscenes, | Guillermo Pinto
cutscenes xml |  | 2017-05-13 | 2017-05-13 | 6 | 100% | 6
height and txt inspection |  | 2017-05-13 | 2017-05-13 | 2 | 100% | 2
enemies on map | Daniel Olondriz
enemies on map |  | 2017-05-13 | 2017-05-13 | 5 | 120% | 6
new forest |  | 2017-05-13 | 2017-05-13 | 3 | 66.67% | 2
boss, maps | Miquel Izquierdo
camera limits |  | 2017-05-13 | 2017-05-13 | 2 | 100% | 2
bug fixing, boss |  | 2017-05-13 | 2017-05-13 | 6 | 100% | 6
NPC | Nicolas babot
save / load |  | 2017-05-13 | 2017-05-13 | 4 | 175% | 7
enemies hurt |  | 2017-05-13 | 2017-05-13 | 2 | 50% | 1
navi implemented |  | 2017-05-13 | 2017-05-13 | 2 | 50% | 1
XML dialogues | Xavier Olivenza
dialogues |  | 2017-05-13 | 2017-05-13 | 6 | 116.7% | 7
memory leaks |  | 2017-05-13 | 2017-05-13 | 3 | 100% | 3
mix of things | Nicolas babot
village path |  | 2017-05-14 | 2017-05-14 | 6 | 116.7% | 7
cartel added |  | 2017-05-14 | 2017-05-14 | 3 | 66.67% | 2
new UI, spritesheet | Daniel Olondriz
UI sprites |  | 2017-05-14 | 2017-05-14 | 3 | 66.67% | 2
Colors cinematic |  | 2017-05-14 | 2017-05-14 | 2 | 100% | 2
smaller village |  | 2017-05-14 | 2017-05-14 | 3 | 100% | 3
spritesheet updated |  | 2017-05-14 | 2017-05-14 | 2 | 50% | 1
maps | Miquel Izquierdo
maps |  | 2017-05-14 | 2017-05-14 | 7 | 85.71% | 6
Boss |  | 2017-05-14 | 2017-05-14 | 3 | 66.67% | 2
UI | Xavier Olivenza
campaign, audio options |  | 2017-05-14 | 2017-05-14 | 3 | 166.7% | 5
dialogues updated |  | 2017-05-14 | 2017-05-14 | 2 | 400% | 8
cutscenes, | Guillermo Pinto
cutscenes xml |  | 2017-05-14 | 2017-05-14 | 5 | 120% | 6
credits | Xavier Olivenza
credits |  | 2017-05-15 | 2017-05-16 | 5 | 120% | 6
Boss bug | Miquel Izquierdo
boss bug, mchanic and npc |  | 2017-05-22 | 2017-05-30 | 6 | 100% | 6
bug fix | Xavier Olivenza
bug fix |  | 2017-05-22 | 2017-05-22 | 3 | 66.67% | 2
dungeon doors | Daniel Olondriz
dungeon dors, |  | 2017-05-22 | 2017-05-22 | 5 | 120% | 6
enemy dead animation | Nicolas babot
enemie dead animation |  | 2017-05-22 | 2017-05-22 | 4 | 75% | 3
fire particles |  | 2017-05-22 | 2017-05-22 | 5 | 120% | 6
License | Xavier Olivenza
license |  | 2017-05-22 | 2017-05-22 | 2 | 200% | 4
particles |  | 2017-06-03 | 2017-06-03 | 2 | 300% | 6
cutscenes, height | Guillermo Pinto
cutscenes, forest height |  | 2017-06-04 | 2017-06-04 | 3 | 133.3% | 4
dungeon doors | Daniel Olondriz
dungeon dors, |  | 2017-06-05 | 2017-06-04 | 2 | 100% | 2
boss cinematic |  | 2017-06-04 | 2017-06-04 | 4 | 150% | 6
Bugs and final polish | Miquel Izquierdo
polish |  | 2017-06-04 | 2017-06-04 | 4 | 150% | 6
Polish manegement | Guillermo Pinto
Polish management |  | 2017-06-04 | 2017-06-04 | 5 | 100% | 5
web page | Javier ortiz
web page |  | 2017-06-04 | 2017-06-06 | 6 | 216.7% | 13
Note on A7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on B7: Task Lead Enter the name of the Task Lead in this column.
Note on C7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.

## Stats
ZELDA: HYRULE CONQUEST
Summit Games
Project Lead: |  |  | Nicolas Babot
Project Start Date: |  |  | 2017-02-13
Member | Department | Hours estimated | Hours | Average Deviation
Nicolas Babot | Leader | 212 | 218 | 103.2%
Xavier Olivenza | UI | 216 | 225 | 108%
Miquel Izquierdo | Code | 210 | 213 | 104.3%
Daniel Olondriz | Art + Audio | 190 | 185 | 100.8%
Guillermo Pinto | Mamnagement | 187 | 188 | 103.1%
Adrian Higuero | QA | 80 | 92 | 114.4%
Javier Ortiz | Design | 90 | 101 | 109.9%
TOTAL |  | 1185 | 1222 | 106.2% | Github

## Miquel Izquierdo
ZELDA: HYRULE CONQUEST
Summit Games
Project Lead: | Miquel Izquierdo ( Code)
Project Start Date: | 2017-02-13 | time axis 2017-02-13 to 2017-06-03
Display Week: | 1 |  |  |  |  | 2017-02-13: Week 1; 2017-02-20: Week 2; 2017-02-27: Week 3; 2017-03-06: Week 4; 2017-03-13: Week 5; 2017-03-20: Week 6; 2017-03-27: Week 7; 2017-04-03: Week 8; 2017-04-10: Week 9; 2017-04-17: Week 10; 2017-04-24: Week 11; 2017-05-01: Week 12; 2017-05-08: Week 13; 2017-05-15: Week 14; 2017-05-22: Week 15; 2017-05-29: Week 16
[6 empty] | 2017-02-13 | [6 empty] | 2017-02-20 | [6 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27 | [6 empty] | 2017-04-03 | [6 empty] | 2017-04-10 | [6 empty] | 2017-04-17 | [6 empty] | 2017-04-24 | [6 empty] | 2017-05-01 | [6 empty] | 2017-05-08 | [6 empty] | 2017-05-15 | [6 empty] | 2017-05-22 | [6 empty] | 2017-05-29
Task | Start | End | hours estimated | % deviation | Hours | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Core engine
Windows Resized | 2017-02-13 | 2017-02-15 | 1 | 100% | 1 | bar: 2017-02-13 T to 2017-02-13 W
Module Scene | 2017-02-14 | 2017-02-16 | 1 | 100% | 1 | bar: 2017-02-13 T to 2017-02-13 W
Players
Player | 2017-02-15 | 2017-02-15 | 1 | 100% | 1
2nd player | 2017-02-15 | 2017-02-16 | 2 | 100% | 2
Players
Player | 2017-02-19 | 2017-02-20 | 2 | 100% | 2
Move Player | 2017-02-19 | 2017-02-22 | 1 | 300% | 3
Players
Pathfinding | 2017-02-21 | 2017-02-24 | 4 | 75% | 3
Players
2 player mode | 2017-02-28 | 2017-02-28 | 3 | 100% | 3
Animation, fade to black
Link animation add | 2017-03-01 | 2017-03-02 | 3 | 100% | 3
Production Plan | Team
Production Plan | 2017-03-02 | 2017-03-06 | 20 | 125% | 25
Movement
Animations for 2 players | 2017-03-07 | 2017-03-07 | 3 | 166.7% | 5
Movement | 2017-03-07 | 2017-03-13 | 6 | 83.33% | 5
Player
character and player reestructured | 2017-03-08 | 2017-03-08 | 4 | 75% | 3
Height and jump
player stats | 2017-03-14 | 2017-03-14 | 2 | 50% | 1
Levels of height | 2017-03-14 | 2017-03-15 | 3 | 100% | 3
Jump | 2017-03-14 | 2017-03-15 | 2 | 100% | 2
zoom
zoom | 2017-03-16 | 2017-03-16 | 3 | 66.67% | 2
bugs | 2017-03-16 | 2017-03-16 | 5 | 20% | 1
Roll and entities
Roll implemented | 2017-03-17 | 2017-03-17 | 3 | 66.67% | 2
Collision and entities | 2017-03-17 | 2017-03-17 | 3 | 100% | 3
player heigth | 2017-03-18 | 2017-03-18 | 1 | 200% | 2
re sized map | 2017-03-18 | 2017-03-19 | 4 | 75% | 3
zelda add
Zelda sprites added | 2017-03-19 | 2017-03-19 | 2 | 50% | 1
zelda jump and roll | 2017-03-19 | 2017-03-19 | 2 | 100% | 2
collision tiles and print | 2017-03-19 | 2017-03-19 | 2 | 50% | 1
Picking zelda
Picking zelda | 2017-03-23 | 2017-03-23 | 2 | 150% | 3
Arrows
Arrows | 2017-03-28 | 2017-03-29 | 5 | 140% | 7
Picking zelda
Animations pivot, maps | 2017-03-30 | 2017-03-30 | 3 | 133.3% | 4
In game
map update, change scene | 2017-03-31 | 2017-04-01 | 2 | 100% | 2
objects with texture | 2017-03-31 | 2017-03-31 | 2 | 50% | 1
more arrows | 2017-03-31 | 2017-04-01 | 1 | 100% | 1
door | 2017-03-31 | 2017-04-01 | 4 | 75% | 3
link, zelda, attack
Link update | 2017-04-01 | 2017-04-01 | 1 | 100% | 1
Zelda Attack | 2017-04-01 | 2017-04-01 | 1 | 100% | 1
Attack timing | 2017-04-01 | 2017-04-01 | 2 | 50% | 1
Bug hunting, pause, draw
fixing bugs | 2017-04-03 | 2017-04-03 | 2 | 50% | 1
pause | 2017-04-03 | 2017-04-03 | 2 | 100% | 2
Draw function | 2017-04-03 | 2017-04-03 | 3 | 66.67% | 2
Bug hunting, pause, draw
Arrows | 2017-04-04 | 2017-04-04 | 1 | 200% | 2
Hits effects | 2017-04-04 | 2017-04-04 | 2 | 100% | 2
Maps | 2017-04-04 | 2017-04-04 | 1 | 200% | 2
Bug hunting, pause, draw
attack bugs | 2017-04-05 | 2017-04-05 | 5 | 80% | 4
Module action
Module action | 2017-04-06 | 2017-04-06 | 2 | 100% | 2
Module action
arrow directions | 2017-04-18 | 2017-04-18 | 3 | 66.67% | 2
Boss
Test room and boos | 2017-04-22 | 2017-04-22 | 3 | 133.3% | 4
boss foots | 2017-04-23 | 2017-04-23 | 3 | 100% | 3
Puzzle
color puzzle | 2017-04-24 | 2017-04-24 | 2 | 150% | 3
fixing collision module
fixing collison module | 2017-04-28 | 2017-04-28 | 1 | 100% | 1
Boss | 2017-04-28 | 2017-05-01 | 7 | 128.6% | 9
maps
maps | 2017-04-30 | 2017-04-30 | 2 | 100% | 2
Boss, bug hunting
boss | 2017-05-06 | 2017-05-06 | 4 | 100% | 4
bug hunting | 2017-05-06 | 2017-05-07 | 4 | 100% | 4
Boss, bug hunting
boss | 2017-05-08 | 2017-05-08 | 6 | 133.3% | 8
Boss
Boss | 2017-05-09 | 2017-05-10 | 8 | 100% | 8
Boss
Boss | 2017-05-11 | 2017-05-11 | 6 | 116.7% | 7
Top of the mountain, path to boss | 2017-05-11 | 2017-05-11 | 2 | 50% | 1
bug fixing
bug fixing | 2017-05-12 | 2017-05-12 | 2 | 50% | 1
Boss, maps | 2017-05-12 | 2017-05-12 | 5 | 140% | 7
boss, maps
camera limits | 2017-05-13 | 2017-05-13 | 2 | 100% | 2
bug fixing, boss | 2017-05-13 | 2017-05-13 | 6 | 100% | 6
maps
maps | 2017-05-14 | 2017-05-14 | 7 | 85.71% | 6
Boss | 2017-05-14 | 2017-05-14 | 3 | 66.67% | 2
Boss bug
boss bug, mchanic and npc | 2017-05-22 | 2017-05-30 | 6 | 100% | 6
Bugs and final polish
polish | 2017-06-04 | 2017-06-04 | 4 | 150% | 6
TOTAL |  |  | 210 | 104.3% | 213
Note on A7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on B7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.

## Xavier Olivenza
ZELDA: HYRULE CONQUEST
Summit Games
Project Lead: | Xavier Olivenza (UI)
Project Start Date: | 2017-02-13 | time axis 2017-02-13 to 2017-06-03
Display Week: | 1 |  |  |  |  | 2017-02-13: Week 1; 2017-02-20: Week 2; 2017-02-27: Week 3; 2017-03-06: Week 4; 2017-03-13: Week 5; 2017-03-20: Week 6; 2017-03-27: Week 7; 2017-04-03: Week 8; 2017-04-10: Week 9; 2017-04-17: Week 10; 2017-04-24: Week 11; 2017-05-01: Week 12; 2017-05-08: Week 13; 2017-05-15: Week 14; 2017-05-22: Week 15; 2017-05-29: Week 16
[6 empty] | 2017-02-13 | [6 empty] | 2017-02-20 | [6 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27 | [6 empty] | 2017-04-03 | [6 empty] | 2017-04-10 | [6 empty] | 2017-04-17 | [6 empty] | 2017-04-24 | [6 empty] | 2017-05-01 | [6 empty] | 2017-05-08 | [6 empty] | 2017-05-15 | [6 empty] | 2017-05-22 | [6 empty] | 2017-05-29
Task | Start | End | hours estimated | % deviation | Hours | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Console Code
Creating the Module console | 2017-02-13 | 2017-02-23 | 25 | 80% | 20
Adding to Project master | 2017-02-24 | 2017-02-24 | 4 | 75% | 3
Window
Window resize | 2017-02-28 | 2017-02-28 | 3 | 66.67% | 2
Production Plan
Production Plan | 2017-03-02 | 2017-03-06 | 20 | 125% | 25
Window
diagrams | 2017-03-07 | 2017-03-07 | 3 | 66.67% | 2
Camara
Elipses and centring | 2017-03-13 | 2017-03-19 | 15 | 113.3% | 17
Camara
zoom camera | 2017-03-19 | 2017-03-19 | 3 | 100% | 3
Gui variablles | 2017-03-19 | 2017-03-20 | 3 | 33.33% | 1
debug mode | 2017-03-19 | 2017-03-21 | 3 | 100% | 3
Menu
Main menu,options | 2017-03-23 | 2017-03-24 | 4 | 125% | 5
HUD
Hud module | 2017-03-27 | 2017-03-27 | 2 | 100% | 2
Life add | 2017-03-28 | 2017-03-28 | 2 | 50% | 1
Intro, mmain menu parralax
background intro, parrallax | 2017-03-29 | 2017-03-29 | 6 | 133.3% | 8
menu atlas
menu atlas | 2017-03-30 | 2017-03-30 | 2 | 50% | 1
social buttons added | 2017-03-30 | 2017-03-30 | 2 | 50% | 1
tiled
tiled | 2017-03-31 | 2017-03-31 | 1 | 100% | 1
in game menu
in game menu | 2017-04-01 | 2017-04-02 | 6 | 116.7% | 7
in game menu
in game menu | 2017-04-03 | 2017-04-03 | 1 | 100% | 1
xml | 2017-04-03 | 2017-04-03 | 1 | 100% | 1
Load code | 2017-04-03 | 2017-04-03 | 3 | 66.67% | 2
Scenes | 2017-04-03 | 2017-04-03 | 1 | 100% | 1
Menu label | 2017-04-04 | 2017-04-04 | 4 | 50% | 2
Backgound | 2017-04-04 | 2017-04-04 | 1 | 200% | 2
HUD | 2017-04-04 | 2017-04-04 | 3 | 66.67% | 2
Menu and music sync
Menu and music sync | 2017-04-05 | 2017-04-05 | 4 | 100% | 4
Coming soon sign
Coming soon sign | 2017-04-06 | 2017-04-06 | 3 | 66.67% | 2
Dialogue manager | 2017-04-06 | 2017-04-07 | 3 | 133.3% | 4
Fran research
Fran research | 2017-04-18 | 2017-04-18 | 4 | 75% | 3
Coming soon sign
Dialogue manager | 2017-04-21 | 2017-04-21 | 6 | 100% | 6
dialogues xml
Dialogues XML | 2017-04-22 | 2017-04-22 | 2 | 100% | 2
items read, npc | 2017-04-22 | 2017-04-23 | 2 | 200% | 4
Quadtree
Quadtree | 2017-04-24 | 2017-04-24 | 2 | 100% | 2
Adapting blit | 2017-04-24 | 2017-04-25 | 1 | 100% | 1
save/load code
save / load | 2017-04-27 | 2017-04-27 | 4 | 100% | 4
quadtree and particles
quadtree and particles | 2017-05-03 | 2017-05-04 | 15 | 80% | 12
camera, atlas, dialogues…
camera fix | 2017-05-06 | 2017-05-06 | 2 | 50% | 1
atlas | 2017-05-06 | 2017-05-06 | 2 | 50% | 1
module dialogue | 2017-05-06 | 2017-05-06 | 2 | 100% | 2
add function | 2017-05-06 | 2017-05-06 | 2 | 100% | 2
menus | 2017-05-06 | 2017-05-06 | 1 | 100% | 1
memory leaks | 2017-05-06 | 2017-05-06 | 1 | 100% | 1
XML dialogues
XML dialogues, NPC, camera | 2017-05-10 | 2017-05-10 | 5 | 120% | 6
alternative controller | 2017-05-10 | 2017-05-10 | 3 | 66.67% | 2
XML dialogues
dialogues, save | 2017-05-11 | 2017-05-12 | 7 | 142.9% | 10
bug fixing | 2017-05-11 | 2017-05-11 | 1 | 100% | 1
XML dialogues
dialogues | 2017-05-13 | 2017-05-13 | 6 | 116.7% | 7
memory leaks | 2017-05-13 | 2017-05-13 | 3 | 100% | 3
UI
campaign, audio options | 2017-05-14 | 2017-05-14 | 3 | 166.7% | 5
dialogues updated | 2017-05-14 | 2017-05-14 | 2 | 400% | 8
credits
credits | 2017-05-15 | 2017-05-16 | 5 | 120% | 6
bug fix
bug fix | 2017-05-22 | 2017-05-22 | 3 | 66.67% | 2
License
license | 2017-05-22 | 2017-05-22 | 2 | 200% | 4
particles | 2017-06-03 | 2017-06-03 | 2 | 300% | 6
TOTAL |  |  | 216 | 108% | 225
Note on A7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on B7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.

## Nicolas Babot
ZELDA: HYRULE CONQUEST
Summit Games
Project Lead: | Nicolas Babot
Project Start Date: | 2017-02-13 | time axis 2017-02-13 to 2017-06-03
Display Week: | 1 |  |  |  |  | 2017-02-13: Week 1; 2017-02-20: Week 2; 2017-02-27: Week 3; 2017-03-06: Week 4; 2017-03-13: Week 5; 2017-03-20: Week 6; 2017-03-27: Week 7; 2017-04-03: Week 8; 2017-04-10: Week 9; 2017-04-17: Week 10; 2017-04-24: Week 11; 2017-05-01: Week 12; 2017-05-08: Week 13; 2017-05-15: Week 14; 2017-05-22: Week 15; 2017-05-29: Week 16
[6 empty] | 2017-02-13 | [6 empty] | 2017-02-20 | [6 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27 | [6 empty] | 2017-04-03 | [6 empty] | 2017-04-10 | [6 empty] | 2017-04-17 | [6 empty] | 2017-04-24 | [6 empty] | 2017-05-01 | [6 empty] | 2017-05-08 | [6 empty] | 2017-05-15 | [6 empty] | 2017-05-22 | [6 empty] | 2017-05-29
Task | Start | End | hours estimated | % deviation | Hours | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Code to STD
Coding STD | 2017-02-16 | 2017-02-17 | 4 | 112.5% | 4.5
Pathfinding | 2017-02-22 | 2017-02-23 | 2 | 100% | 2
Window
Animation, fade to black | 2017-02-24 | 2017-02-24 | 2 | 100% | 2
Camera limits | 2017-02-24 | 2017-02-25 | 4 | 100% | 4
Production Plan
Production Plan | 2017-03-02 | 2017-03-06 | 20 | 125% | 25
Menu
Enable disable menu | 2017-03-13 | 2017-03-13 | 3 | 66.67% | 2
Collider
Logic | 2017-03-14 | 2017-03-16 | 2 | 100% | 2
M.Collision | 2017-03-14 | 2017-03-16 | 3 | 100% | 3
Link Collider | 2017-03-14 | 2017-03-16 | 3 | 66.67% | 2
Height Collider | 2017-03-14 | 2017-03-16 | 2 | 100% | 2
Buttons
Buttons implemented | 2017-03-18 | 2017-03-18 | 3 | 66.67% | 2
coperative & culling
cooperartive game | 2017-03-19 | 2017-03-19 | 2 | 150% | 3
Camera culling | 2017-03-19 | 2017-03-21 | 5 | 80% | 4
Enemies
Enemies, enemies by tiles | 2017-03-23 | 2017-03-28 | 12 | 125% | 15
Enemies
Sword collision | 2017-03-29 | 2017-03-29 | 8 | 75% | 6
Enemies
Sword-enemies collision | 2017-03-30 | 2017-03-30 | 2 | 100% | 2
Enemies
Enemies | 2017-03-31 | 2017-03-31 | 3 | 66.67% | 2
pathfinding
pathfinding | 2017-04-01 | 2017-04-01 | 3 | 166.7% | 5
audio and enemy
Audio | 2017-04-01 | 2017-04-01 | 2 | 100% | 2
enemy path | 2017-04-01 | 2017-04-02 | 3 | 100% | 3
audio and enemy
Controls | 2017-04-02 | 2017-04-02 | 1 | 200% | 2
bug hunting, player collider
bug fixing | 2017-04-03 | 2017-04-03 | 2 | 150% | 3
player collider | 2017-04-03 | 2017-04-03 | 3 | 100% | 3
Loop, life, sound effect
Loop | 2017-04-04 | 2017-04-04 | 2 | 100% | 2
Life add | 2017-04-04 | 2017-04-04 | 1 | 200% | 2
Sound Efect | 2017-04-04 | 2017-04-04 | 2 | 100% | 2
bugs, collider
Collider | 2017-04-05 | 2017-04-05 | 5 | 80% | 4
Green Enemy
Green Enemy | 2017-04-16 | 2017-04-16 | 3 | 100% | 3
Green Enemy
Green Enemy | 2017-04-17 | 2017-04-19 | 5 | 80% | 4
Green Enemy
enemies, shield bomb | 2017-04-21 | 2017-04-21 | 8 | 75% | 6
bomb enemy | 2017-04-22 | 2017-04-22 | 4 | 75% | 3
Green Enemy
Enemies Collision | 2017-04-23 | 2017-04-23 | 4 | 75% | 3
Enemies
On collisionn | 2017-04-27 | 2017-04-27 | 2 | 100% | 2
Arnus enemy | 2017-04-27 | 2017-04-27 | 3 | 100% | 3
testing scenes and sprites
testing scenes and adding spirtes | 2017-04-28 | 2017-04-28 | 2 | 100% | 2
Scenes | 2017-04-29 | 2017-04-29 | 3 | 200% | 6
arnus snake
arnus snake | 2017-04-30 | 2017-05-01 | 2 | 150% | 3
cutscenes, enemy
cutscenes, enemy | 2017-05-06 | 2017-05-08 | 12 | 133.3% | 16
enemy
enemy path | 2017-05-09 | 2017-05-09 | 5 | 100% | 5
maps, tiles and fixing, cutscenes
tile, cameras, maps | 2017-05-10 | 2017-05-10 | 5 | 120% | 6
cutscenes | 2017-05-10 | 2017-05-10 | 3 | 66.67% | 2
NPC and cutscenes
NPC, helping and cutscenes | 2017-05-11 | 2017-05-11 | 8 | 100% | 8
NPC
NPC | 2017-05-12 | 2017-05-12 | 3 | 133.3% | 4
save / load | 2017-05-12 | 2017-05-12 | 5 | 80% | 4
NPC
save / load | 2017-05-13 | 2017-05-13 | 8 | 87.5% | 7
enemies hurt | 2017-05-13 | 2017-05-13 | 2 | 50% | 1
navi implemented | 2017-05-13 | 2017-05-13 | 2 | 50% | 1
mix of things
village path | 2017-05-14 | 2017-05-14 | 6 | 116.7% | 7
cartel added | 2017-05-14 | 2017-05-14 | 3 | 66.67% | 2
enemy dead animation
enemie dead animation | 2017-05-22 | 2017-05-22 | 4 | 75% | 3
fire particles | 2017-05-22 | 2017-05-22 | 6 | 100% | 6
TOTAL |  |  | 212 | 103.2% | 217.5
Note on A7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on B7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.

## Daniel Olondriz
ZELDA: HYRULE CONQUEST
Summit Games
Project Lead: | Daniel Olondriz (Art+Audio)
Project Start Date: | 2017-02-13 | time axis 2017-02-13 to 2017-06-03
Display Week: | 1 |  |  |  |  | 2017-02-13: Week 1; 2017-02-20: Week 2; 2017-02-27: Week 3; 2017-03-06: Week 4; 2017-03-13: Week 5; 2017-03-20: Week 6; 2017-03-27: Week 7; 2017-04-03: Week 8; 2017-04-10: Week 9; 2017-04-17: Week 10; 2017-04-24: Week 11; 2017-05-01: Week 12; 2017-05-08: Week 13; 2017-05-15: Week 14; 2017-05-22: Week 15; 2017-05-29: Week 16
[6 empty] | 2017-02-13 | [6 empty] | 2017-02-20 | [6 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27 | [6 empty] | 2017-04-03 | [6 empty] | 2017-04-10 | [6 empty] | 2017-04-17 | [6 empty] | 2017-04-24 | [6 empty] | 2017-05-01 | [6 empty] | 2017-05-08 | [6 empty] | 2017-05-15 | [6 empty] | 2017-05-22 | [6 empty] | 2017-05-29
Task | Start | End | hours estimated | % deviation | Hours | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Extracting Sprites
Overworld Spriites | 2017-02-14 | 2017-02-14 | 10 | 70% | 7
Overworld Spriites | 2017-02-14 | 2017-02-15 | 6 | 83.33% | 5
Overworld tileset
change tileset | 2017-02-18 | 2017-02-18 | 1 | 200% | 2
dungeon tileset | 2017-02-18 | 2017-02-19 | 2 | 100% | 2
Boss design | 2017-02-18 | 2017-02-26 | 20 | 100% | 20
Production Plan
Production Plan | 2017-03-02 | 2017-03-06 | 20 | 125% | 25
zelda
Zelda sprites | 2017-03-19 | 2017-03-19 | 3 | 133.3% | 4
Graphic Menu
Graphic menu | 2017-03-28 | 2017-03-28 | 3 | 100% | 3
dungeon tileset
dungeon tileset | 2017-03-29 | 2017-03-29 | 5 | 80% | 4
dungeon tileset
Dunngeon tileset | 2017-03-30 | 2017-03-30 | 3 | 100% | 3
collision tileset | 2017-03-30 | 2017-03-31 | 4 | 125% | 5
spritesheet link
spritesheet link | 2017-04-01 | 2017-04-01 | 1 | 200% | 2
sprites
Zelda (blue link) | 2017-04-02 | 2017-04-02 | 2 | 50% | 1
Dianas | 2017-04-02 | 2017-04-02 | 1 | 100% | 1
Bow | 2017-04-02 | 2017-04-02 | 5 | 40% | 2
controls menu | 2017-04-02 | 2017-04-02 | 1 | 100% | 1
Game loop art, scenes
Game loop art | 2017-04-03 | 2017-04-03 | 4 | 75% | 3
Scenes | 2017-04-03 | 2017-04-03 | 2 | 150% | 3
door sprites, title and controls
Door sprites | 2017-04-04 | 2017-04-04 | 1 | 100% | 1
Title sprites | 2017-04-04 | 2017-04-04 | 2 | 100% | 2
Controls | 2017-04-04 | 2017-04-04 | 1 | 100% | 1
Button sprites, audio
Button sprites, audio | 2017-04-05 | 2017-04-05 | 5 | 80% | 4
Items and overworld tileset
items and overworld tileset | 2017-04-14 | 2017-04-14 | 4 | 75% | 3
Dialogues illustration
Dialogue illustration | 2017-04-24 | 2017-04-26 | 6 | 83.33% | 5
Dialogues illustration
Dialogue illustration | 2017-04-27 | 2017-04-27 | 6 | 100% | 6
zelda sprites
zelda spites | 2017-04-29 | 2017-04-29 | 6 | 100% | 6
Dialogues illustration
Dialogue illustration | 2017-05-06 | 2017-05-06 | 4 | 100% | 4
Dialogues illustration
Dialogue illustration | 2017-05-07 | 2017-05-07 | 4 | 175% | 7
Dialogues illustration
Dialogue illustration | 2017-05-09 | 2017-05-09 | 8 | 75% | 6
Dialogues illustration
Dialogue illustration | 2017-05-10 | 2017-05-10 | 4 | 75% | 3
Intro and sounds | 2017-05-10 | 2017-05-10 | 3 | 166.7% | 5
cinematics
cinematics | 2017-05-11 | 2017-05-11 | 6 | 66.67% | 4
music to OGG | 2017-05-11 | 2017-05-11 | 6 | 83.33% | 5
enemies on map
enemies on map | 2017-05-13 | 2017-05-13 | 5 | 120% | 6
new forest | 2017-05-13 | 2017-05-13 | 3 | 66.67% | 2
new UI, spritesheet
UI sprites | 2017-05-14 | 2017-05-14 | 3 | 66.67% | 2
Colors cinematic | 2017-05-14 | 2017-05-14 | 2 | 100% | 2
smaller village | 2017-05-14 | 2017-05-14 | 3 | 100% | 3
spritesheet updated | 2017-05-14 | 2017-05-14 | 2 | 50% | 1
dungeon doors
dungeon dors, | 2017-05-22 | 2017-05-22 | 5 | 120% | 6
dungeon doors
dungeon dors, | 2017-06-05 | 2017-06-04 | 2 | 100% | 2
boss cinematic | 2017-06-04 | 2017-06-04 | 6 | 100% | 6
TOTAL |  |  | 190 | 100.8% | 185
Note on A7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on B7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.

## Guillermo Pinto
ZELDA: HYRULE CONQUEST
Summit Games
Project Lead: | Guillermo Pinto (Management)
Display Week: | 2017-02-13 | time axis 2017-02-13 to 2017-06-03
Display Week: | 1 |  |  |  |  | 2017-02-13: Week 1; 2017-02-20: Week 2; 2017-02-27: Week 3; 2017-03-06: Week 4; 2017-03-13: Week 5; 2017-03-20: Week 6; 2017-03-27: Week 7; 2017-04-03: Week 8; 2017-04-10: Week 9; 2017-04-17: Week 10; 2017-04-24: Week 11; 2017-05-01: Week 12; 2017-05-08: Week 13; 2017-05-15: Week 14; 2017-05-22: Week 15; 2017-05-29: Week 16
[6 empty] | 2017-02-13 | [6 empty] | 2017-02-20 | [6 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27 | [6 empty] | 2017-04-03 | [6 empty] | 2017-04-10 | [6 empty] | 2017-04-17 | [6 empty] | 2017-04-24 | [6 empty] | 2017-05-01 | [6 empty] | 2017-05-08 | [6 empty] | 2017-05-15 | [6 empty] | 2017-05-22 | [6 empty] | 2017-05-29
Task | Start | End | hours estimated | % deviation | Hours | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Link sprites extract
Link sprites | 2017-02-14 | 2017-02-15 | 8 | 62.5% | 5
Trello, github and management
Trello,github and management tools | 2017-02-18 | 2017-02-18 | 5 | 120% | 6
Link sprites extract
Link sprites extract | 2017-02-20 | 2017-02-28 | 15 | 80% | 12
Production Plan
Production Plan | 2017-03-02 | 2017-03-06 | 20 | 125% | 25
Link sprites
Link sprites, bigger | 2017-03-13 | 2017-03-13 | 6 | 100% | 6
Link sprites
Link sprites, bigger | 2017-03-16 | 2017-03-16 | 6 | 100% | 6
item tileset
item tileset | 2017-03-19 | 2017-03-19 | 6 | 83.33% | 5
Link sprites
Link sprites, bigger | 2017-03-16 | 2017-03-16 | 5 | 60% | 3
throwing zelda | 2017-03-23 | 2017-03-27 | 2 | 150% | 3
item tileset
item tileset | 2017-03-29 | 2017-03-29 | 5 | 80% | 4
link spritesheet
link spritesheet | 2017-03-30 | 2017-03-31 | 5 | 120% | 6
spritesheet
enemies spritesheets | 2017-04-02 | 2017-04-02 | 5 | 120% | 6
init variables to zero
initing variables | 2017-04-02 | 2017-04-02 | 2 | 150% | 3
code to STD | 2017-04-02 | 2017-04-02 | 4 | 75% | 3
Link sprites, bigger
Link spritesheets | 2017-04-04 | 2017-04-05 | 12 | 83.33% | 10
Tilesets created
Tileset created | 2017-04-14 | 2017-04-14 | 7 | 85.71% | 6
Dungeon, int and ex castle
Tilesets created | 2017-04-24 | 2017-04-24 | 6 | 100% | 6
Cave tileset | 2017-04-24 | 2017-04-25 | 2 | 150% | 3
Enemies spritesheet hit
Enemies spritesheet hit | 2017-04-26 | 2017-04-26 | 2 | 150% | 3
Enemies spritesheet hit
secret exit map | 2017-05-06 | 2017-05-06 | 4 | 150% | 6
Zelda XML
Zelda xml pivot | 2017-05-07 | 2017-05-07 | 2 | 100% | 2
Inside house
insidue house | 2017-05-08 | 2017-05-08 | 8 | 100% | 8
before dungeon and puzzle
before dungeon and puzzle | 2017-05-09 | 2017-05-09 | 6 | 66.67% | 4
before dungeon and puzzle
navy sprites and lake | 2017-05-10 | 2017-05-10 | 4 | 100% | 4
throne room added | 2017-05-10 | 2017-05-10 | 3 | 133.3% | 4
cutscenes,
cutscenes xml | 2017-05-11 | 2017-05-12 | 16 | 100% | 16
cutscenes,
cutscenes xml | 2017-05-13 | 2017-05-13 | 6 | 100% | 6
height and txt inspection | 2017-05-13 | 2017-05-13 | 2 | 100% | 2
cutscenes,
cutscenes xml | 2017-05-14 | 2017-05-14 | 5 | 120% | 6
cutscenes, height
cutscenes, forest height | 2017-06-04 | 2017-06-04 | 3 | 133.3% | 4
Polish manegement
Polish management | 2017-06-04 | 2017-06-04 | 5 | 100% | 5
TOTAL |  |  | 187 | 103.1% | 188
Note on A7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on B7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.

## Adrian Higuero
ZELDA: HYRULE CONQUEST
Summit Games
Project Lead: | Adrian Higuero (QA)
Project Start Date: | 2017-02-13 | time axis 0 to 2017-06-03
Display Week: | 3 |  |  |  |  | 0: Week 1; 2017-02-20: Week 2; 2017-02-27: Week 3; 2017-03-06: Week 4; 2017-03-13: Week 5; 2017-03-20: Week 6; 2017-03-27: Week 7; 2017-04-03: Week 8; 2017-04-10: Week 9; 2017-04-17: Week 10; 2017-04-24: Week 11; 2017-05-01: Week 12; 2017-05-08: Week 13; 2017-05-15: Week 14; 2017-05-22: Week 15; 2017-05-29: Week 16
[6 empty] | 2017-02-13 | [6 empty] | 2017-02-20 | [6 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27 | [6 empty] | 2017-04-03 | [6 empty] | 2017-04-10 | [6 empty] | 2017-04-17 | [6 empty] | 2017-04-24 | [6 empty] | 2017-05-01 | [6 empty] | 2017-05-08 | [6 empty] | 2017-05-15 | [6 empty] | 2017-05-22 | [6 empty] | 2017-05-29
Task | Start | End | hours estimated | % deviation | Hours | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Production Plan
Production Plan | 2017-03-02 | 2017-03-06 | 20 | 125% | 25
bug hunting
bug hunting | 2017-03-13 | 2017-03-19 | 3 | 100% | 3
bug hunting
bug hunting | 2017-03-16 | 2017-03-16 | 3 | 100% | 3
bug hunting
bug hunting | 2017-03-23 | 2017-03-23 | 3 | 100% | 3
bug hunting
bug hunting | 2017-03-28 | 2017-03-28 | 3 | 100% | 3
bug hunting
bug hunting | 2017-03-30 | 2017-03-30 | 3 | 100% | 3
Appveyor
Appveyor implementation | 2017-04-02 | 2017-04-02 | 2 | 100% | 2
Bug hunting
Bug hunting | 2017-04-03 | 2017-04-03 | 3 | 166.7% | 5
bug hunting
bug hunting | 2017-04-04 | 2017-04-04 | 3 | 133.3% | 4
bug hunting
bug hunting | 2017-04-06 | 2017-04-06 | 3 | 133.3% | 4
Dialogues
Dialogues | 2017-04-23 | 2017-04-25 | 10 | 100% | 10
Dialogues
Dialogues | 2017-04-25 | 2017-04-29 | 8 | 125% | 10
Dialogues
Dialogues | 2017-05-01 | 2017-05-01 | 4 | 100% | 4
Dialogues
Dialogues | 2017-05-08 | 2017-05-09 | 9 | 100% | 9
bug hunting
bug hunting | 2017-05-11 | 2017-05-11 | 3 | 133.3% | 4
TOTAL |  |  | 80 | 114.4% | 92
Note on A7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on B7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.

## Javier Ortiz
ZELDA: HYRULE CONQUEST
Summit Games
Project Lead: |  | Javier Ortiz (Design)
Project Start Date: |  | 2017-02-13 | time axis 2017-02-13 to 2017-06-03
Display Week: |  | 1 |  |  |  |  | 2017-02-20: Week 2; 2017-02-27: Week 3; 2017-03-06: Week 4; 2017-03-13: Week 5; 2017-03-20: Week 6; 2017-03-27: Week 7; 2017-04-03: Week 8; 2017-04-10: Week 9; 2017-04-17: Week 10; 2017-04-24: Week 11; 2017-05-01: Week 12; 2017-05-08: Week 13; 2017-05-15: Week 14; 2017-05-22: Week 15; 2017-05-29: Week 16
[7 empty] | 2017-02-13 | [6 empty] | 2017-02-20 | [6 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27 | [6 empty] | 2017-04-03 | [6 empty] | 2017-04-10 | [6 empty] | 2017-04-17 | [6 empty] | 2017-04-24 | [6 empty] | 2017-05-01 | [6 empty] | 2017-05-08 | [6 empty] | 2017-05-15 | [6 empty] | 2017-05-22 | [6 empty] | 2017-05-29
Task | Lead | Start | End | hours estimated | % deviation | Hours | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Production Plan | Team
Production Plan |  | 2017-03-02 | 2017-03-06 | 20 | 125% | 25
Gamepad | Javier ortiz
Gamepad |  | 2017-03-15 | 2017-03-16 | 3 | 133.3% | 4
Game puzzles | Javier ortiz
Game puzzles |  | 2017-03-15 | 2017-03-16 | 6 | 66.67% | 4
Gamepad | Javier ortiz
second gamepad |  | 2017-03-24 | 2017-03-24 | 4 | 75% | 3
Puzzles | Javier ortiz
1rst puzzle |  | 2017-03-28 | 2017-03-30 | 2 | 100% | 2
2nd puzzle |  | 2017-03-28 | 2017-03-30 | 2 | 100% | 2
3rd puzzle |  | 2017-03-28 | 2017-03-30 | 3 | 100% | 3
Gamepad | Javier ortiz
gamepad |  | 2017-03-30 | 2017-03-31 | 4 | 75% | 3
Tileset puzzles | Javier ortiz
tileset puzzle 1 |  | 2017-04-02 | 2017-04-02 | 2 | 150% | 3
tileset puzzle 2 |  | 2017-04-02 | 2017-04-02 | 3 | 133.3% | 4
Gamepad | Javier ortiz
gamepad |  | 2017-04-03 | 2017-04-03 | 5 | 80% | 4
Gamepad | Javier ortiz
gamepad |  | 2017-04-04 | 2017-04-04 | 3 | 100% | 3
tileset village | Javier ortiz
tileset village |  | 2017-04-06 | 2017-04-10 | 10 | 120% | 12
design dungeon | Javier ortiz
design dungeon |  | 2017-04-17 | 2017-04-19 | 3 | 100% | 3
tileset woods | Javier ortiz
tileset woods |  | 2017-04-22 | 2017-04-22 | 4 | 150% | 6
Puzzle color | Javier ortiz
Puzzle color |  | 2017-04-24 | 2017-04-24 | 2 | 100% | 2
Second control setting | Javier ortiz
Second control setting |  | 2017-05-09 | 2017-05-09 | 2 | 100% | 2
bug hunting |  | 2017-05-10 | 2017-05-10 | 2 | 150% | 3
web page | Javier ortiz
web page |  | 2017-06-04 | 2017-06-06 | 10 | 130% | 13
TOTAL |  |  |  | 90 | 109.9% | 101
Note on A7: Task Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on B7: Task Lead Enter the name of the Task Lead in this column.
Note on C7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.